PROTOCOL FOR MAINTENANCE WORKS

PART I : Funding of Maintenance Works and General Guidelines for Planned and Emergency Work ### PART II : PROTOCOL FOR MAINTENANCE WORK: BUILDINGS AND INSTALLED ENGINEERING SERVICES

OBJECTIVE: To regulate and standardize the procedures to be followed when maintenance work is carried out.

Compiled by the Directorate Engineering and Technical Support

Date	:	2013

Signed	:	CF Badenhorst – Chief Engineer

PROTOCOL FOR MAINTENANCE WORK

INTRODUCTION

Due to many reasons, including financial constraints, the Institution’s workshop staff and the budgeted expenditure for maintenance work has become a frontline casualty in the struggle to remain within the budget.

Costs of repair and maintenance have escalated far beyond that which normally would have been sufficient had there been adequate staffing, proper systems and procedures in place within the Institutions.

As a result of staff shortages, institutions are not able to do adequate Preventive Maintenance and only broken equipment and facilities are repaired or serviced, i.e. “wait to break”. Note should however be taken of the Preventative maintenance program being implemented at New facilities.

Many institution managers attempt to obtain savings by cutting that part of the budget relating to equipment maintenance, repair and training.  The result is inevitably an increase in equipment related expenditure due to breakages, shortened life cycle and increased frustration of medical staff.

It is estimated that there is a 50 – 80% reduction in the useful lifetime of a piece of equipment due to operator misuse and lack of maintenance and repair.

About 50% of all equipment experiences excessive downtime due to lack of preventive maintenance, inexperience in repair and lack of spares.

Many institutions do not realize that the equipment maintenance budget must support the capital investment, and as a consequence no budgetary provision is made for the maintenance of new equipment.

Within the Health Care environment, maintenance must be considered as a factor of production; whose product is the quality of health.

The inability to maintain a piece of medical equipment (properly) may result not only in financial losses, but also loss of life and quality of health care delivery.

It is crucial to understand that maintenance and training should not be the first option to cut in order to try to obtain small short term savings, which will translate into very large long term losses.

This protocol for maintenance work is divided into 2 parts:

Part I 	refers to funding and General Guidelines

#### PART I	-	FUNDING OF MAINTENANCE WORKS AND GENERAL GUIDELINES FOR PLANNED, PREVENTATIVE AND EMERGENCY WORK

- From 1st April 2012 the funds for the Scheduled maintenance work to be carried out by Department of Transport and Public Works has been placed with Health under program 8 ( Directorate: Infrastructure planning).

There are now, 4 types of funding for maintenance work of buildings, associated facilities and equipment:

  - Hospitals / Institutions maintenance funds for the work carried out, mainly, by the hospital’s / institution’s workshop staff, i.e. day-to-day maintenance / repairs, and preventive maintenance (Institutions Budgets i.e. Program 1 to 7).

  - Day-to-day professional maintenance projects (previously Ad-Hoc) Program 7.2 for:

    - The work carried out, mainly, by the Mobile Workshops staff of Bellville, Zwaanswyk and Goodwood (Clinical Engineering).

    - The work carried out, by the hospital’s / institution’s workshop staff, but their funds are insufficient to cover the more expensive works.

    - The work carried out by “contractors”, appointed either by the Directorate: Engineering and Technical Support or appointed directly by the hospital’s / institution’s workshop, after authorization from the Directorate: Engineering and Technical Support.

  - Emergency Maintenance Work of Buildings and Installed Engineering Services (excluding equipment), Program 7.2

    - Emergency repairs are limited to works, authorized by the Chief Engineer, and carried out by “contractors” appointed and managed either by the Institution or by the Directorate Engineering and Technical Support.

    - The funds with reference numbers will be allocated for emergency repairs when it is necessary.  This assistance can be in the form of either:

    - Buying the materials / spare parts and the work is done by the hospital / institution workshop or;

    - Buying the materials / spare parts and the work is done by the Mobile Workshop’s staff or;

    - The work is done by “contractors” appointed and managed by the hospital / institution and reimbursed from the emergency funds, or;

    - The work is done by “contractors”, appointed and managed by the Directorate Engineering and Technical Support and paid for from the emergency funds.

  - Preventative Maintenance Program 8

    - Preventative Maintenance is a conditional grant and is limited to new Health facilities or facilities which formed part of the Hospital Revitalization Program.  Also included are the Academic Hospitals.  Authorized by the Chief Director: Infrastructure and carried out by “contractors” appointed and managed by the Directorate: Engineering and Support Services, Office of the Chief Engineer.

  - Head Office Health funds, Program 8, for.

    - Planned (Scheduled) Maintenance Work of Buildings and Installed Engineering Services (excluding equipment), authorized by the Director: Infrastructure Planning and carried out by “contractors” appointed and managed by the Department of Transport and Public Works.

- The “old concept of dumping” larger repair works on Department of Transport and Public Works and Sub-directorate: Technical Services, falls away.

There has been in many instances the abuse of the hospital / institution workshop staff doing nothing when the repair is needed, waiting for it to escalate and then dumping it on the Department of Transport and Public Works or an “Ad-Hoc” list.

Preventative- and minor repairs are further hampered by lack of SCM support

Continuing to do this is like shooting ourselves in the foot.  The right procedure shall be:

  - When faced with the need of a repair / maintenance work, the hospital’s workshop staff must ask themselves the following questions:

    - Can we do it with the staff and expertise at our disposal, or not?  If yes, do it.

    - Can we do it with our own maintenance funds, or not?  If yes, do it.

  - If NOT, either because the workshop staff is not capable of doing it, or because the hospitals / institutions funds are not enough, then, and only then, it must be referred to the Directorate Engineering and Technical Support for help.

- The Directorate: Engineering and Technical Support will assist with, either:

  - Doing it with the mobile workshops staff

  - Doing it with outside contractors, and paying for it, or

  - Paying for it, but the work must be done by the hospital / institution workshop staff.

- The Directorate: Engineering and Technical Support, will monitor and assess all requests to prevent such abuses as:

  - Dumping work on the mobile workshops (or calling for outside contractors) when the hospitals staff could do it.

  - Requesting for the work to be funded by the Directorate: Engineering and Technical Support, when the amounts should be clearly within the scope of the hospital / institution maintenance budget.

- This protocol is designed mainly with the purpose of regulating, informing all stakeholders, and standardizing, the procedures to be followed when the maintenance work is carried out or funded by Directorate: Engineering and Technical services.

Because the funds for this type of work has been placed with Engineering and Technical services, it is of the utmost necessity that the right procedures be followed strictly and as a matter of urgency, by hospital / institutions staff.

- Planned maintenance funds Program 8 for the maintenance work of buildings and installed engineering services (excluding equipment), by Department of Transport and Public Works.

  - This type of fund is to cover the planned (scheduled) maintenance work (excluding equipment), carried out by “contractors” appointed and managed by Department of Transport and Public Works in the case of Planned maintenance, and appointed and managed by the Department of Transport and Public Works

  - These Funds are allocated by the Directorate Infrastructure planning: Head Office every year, by regions and by hospitals / institutions, in order that every one knows what the allocated budget is.

  - The funds allocated for planned maintenance determine the amount of work to be carried out for that financial year, by contractors appointed and managed by the Department of Transport and Public Works.

8.	Standby and Overtime – Engineering Staff

8.1	Standby duties must continue at all hospitals, as artisan staff must be available to assist when emergency situations occur.

8.2	The standby should be spread between as many of the workshop staff as possible.

  - Standby should preferable be done by artisans who have a good all-round knowledge.  In smaller hospitals it is also acceptable to use competent Senior General Foremen.

8.4	It is not necessary for the artisan on standby to live on the premises as long as he is within a reasonable distance of the hospital.

8.5	He should preferable make use of his own transport and be re-imbursed as per the laid down rates.

8.6	If he does not have transport the hospital can make use of official transport to fetch him.

8.7	Standby should be done on a weekly basis, in rotation.

8.8	When called out overtime starts immediately the staff member leaves home and continuous until he returns home.

8.9	Call outs must be backed up by a “Works Requisition” signed by the Sister-in-charge and must indicate the time the artisan arrives at the hospital and the time the artisan leaves.

8.10	Artisan staff are only to be called out in genuine cases of emergency.

8.11	Although each hospital might have certain special situations which would/could be regarded as an emergency the following may serve as a guideline.

8.12	Any situation, which directly affects the safety of the patients and staff and the safe operation of the hospital.

8.13	Fire

8.14	Major electrical power failures.

8.15	Boiler breakdowns as these affect:	autoclaving

:	cooking

:	central heating

:	air conditioning

8.16	Burst water pipes

8.17	Major sewerage problems (health hazard)

8.18	NOTE:	Nursing staff’s co-operation is imperative to ensure that all unnecessary callouts are avoided.

### PART II	-	PROTOCOL FOR MAINTENANCE WORK:

BUILDINGS AND INSTALLED ENGINEERING SERVICES

- There are Four types of maintenance work of Buildings and Installed Engineering Services:

  - Maintenance work by hospital workshops

  - Maintenance work by the mobile workshops of the Sub Directorate Engineering and Technical Support, and

  - Preventative maintenance (Program 8) funded by Directorate Engineering and Technical Support

  - Maintenance work by controlled by Directorate Infrastructure Planning and executed by Department of Transport and Public Works

- Maintenance Work By Hospital Workshops

  - The hospital workshops are responsible for day-to-day maintenance work, as well as preventative maintenance.  It includes the routine maintenance component of all service contracts.

  - The hospital is responsible for budgeting for day-to-day repairs and preventive maintenance.

  - Department of Transport and Public Works will not carry out day-to-day repairs and preventive maintenance.

  - All costs in respect of the maintenance and repair of equipment are for the account of the hospital concerned or the Sub Directorate Technical Services.  Funding for the maintenance of equipment is budgeted for by the Department of Health.

- Maintenance work by the mobile workshops of the Sub Directorate Engineering and Technical Support

  - Whenever it is not possible for repairs and maintenance work to be carried out by the hospital workshop, either because of a lack of funds due to high cost, or lack of staff and expertise, then the work will be assisted by the Mobile Workshops of Bellville and Zwaanswyk (for General engineering) and Goodwood (for medical equipment, Clinical engineering).

  - The assistance will either be by providing the funds for the work to be carried out by the hospital workshop staff or by doing the necessary repairs with the assistance of the mobile workshop staff, whenever necessary.

- Day-to-Day Professional Maintenance Projects.

[Previously: Ad-Hoc]

  - The maintenance projects scheduled by the Directorate: Engineering and Technical Services, work only refers to the repairs and renovations to buildings and installed engineering services.

  - Installed Engineering Services are those services that were installed as part of the original building contract.

  - Hospital equipment, and day-to-day repairs and minor preventive maintenance of buildings and installed engineering services are thus excluded.

  - The procedure to have Day-to-Day Professional Maintenance Projects Scheduled is as follows:

    - In August every year the designated person in each region invite Medical Superintendents to submit a schedule of “Ad-Hoc” maintenance work.

    - These schedules are then prioritized by the Regional Directors and a prioritized list of Works is then submitted to the Deputy Director: Technical Services (Mr. I Fortuin). (The relevant priority categories are attached hereto – Annexure 3.)

    - After the budget funds for the next financial year are known, the Directorate: Engineering and Technical Services’ committee shall determine an allocation of funds for each Geographical Area.

    - After the allocation of funds, the Deputy Director: Technical Services (Mr. I Fortuin) presents the priority lists to the Regional Directors for comment and/or acceptance.  The priority lists are finalized in March taking into consideration the funds allocated and the priority of the work.

    - All planned (scheduled) maintenance work must have a Works Plan with the Project Scope and the main activities and milestones start and ending times. Eg dates for, Specification complete, advertising date, closing date, order date and completion date.

This Work Plan, must be produced before the actual work starts, and must be signed off by the Hospital Management, the Project Manager and the Directorate Engineering and Technical services representative.

Only then will reference numbers be issued.

    - Institutions will compile a monthly progress report of these projects. This progress report is to be submitted to Deputy Director: Technical Services (Mr. I Fortuin), to review the progress on the scheduled work, and monitor expenditure of planned and emergency work.

    - The Deputy Director: Technical Services (Mr. I Fortuin) will then visit, the Regional Directors each month, to present and review with them, the monthly progress report.

- Emergency repair work

  - Each hospital must have a list of reliable and competent electrical, mechanical, plumbing and building contractors, in their area, which can be called on to carry out emergency work.  These contractors must be registered on the Western Cape Supplier’s Data Base.

  - Definition and instructions re emergencies in accordance with PTI 16 B:

  - Procedures for requesting emergency work

If the hospital is not able to resolve the emergency themselves or funding could be a problem then they must notify Cornel Badenhorst (076-8176156) or Hein Grebe (071-3537226) as soon as possible of the emergency to obtain telephonic assistance / approval.  This must be followed up with a written request using the attached ‘Request for Emergency’ form, which must be faxed to (021) 9181690 or e-mailed to Lucille.Welgemoed@westerncape.gov.za (ANNEXURE 1).

  - Attached is a list of contractors who are familiar with hospital maintenance and repair work with contact details and their field/s of expertise who could be used, in genuine cases of emergency (ANNEXURE 2).  This list will be replaced in future in some areas with a list of contractors whom has entered into a SLA with the department for the execution of emergency repair services.

- Financial Procedures for Day-to-day Professional maintenance projects (DPMP) and emergency repair work

  - Hospital to issue order against Emergency Delegation – see Supply Chain Management (SCM) Regulations or in the case of DPMP after following normal SCM procedures

  - Hospitals are to comply with the requirements of the PFMA and SCM, Regulations.

  - Hospitals are to place the necessary orders and pay for the work done, and then submit the claim to the Assistant Director:  Accounting, Bellville Mobile Workshops.

Such maintenance payments are for Day-to-day Professional maintenance projects and emergency work as described in paragraph 5 and PTI 16 B.

    - Regions/Institutions must claim all monies paid to suppliers in respect of the above from Program 7.2.

    - The completed Fin.448 form, together with certified copies of the invoices and the Complete Logis Payment Package (Pakkie) must be submitted to –

The Director:  Engineering and Technical Support

Department of Health

Private Bag X21

Parrow

7499

(For attention:  Ms D Martin, Finance, Bellville Mobile Workshops)

    - The following allocation is to be used when completing the Fin.448 form and reference should be made to this Finance Instruction when submitting the claim.

Fund	:	Assets & Liabilities

Resp.	:	Financial Accounting (H/O)

Obj.	:	Liabilities

Item	:	Inter Respons Clearing Acc

Proj No	:	A + L

Special note -

    - The Directorate Financial Account will only honour claims which are submitted within two months of receipt of invoice.

    - All Claims shall be submitted within 30 days of payment.

    - All claims must be submitted before the end of the financial year.

- Preventative Maintenance Projects.

  - The Preventative maintenance projects are scheduled by the Directorate: Engineering and Technical Services, work only refers to regular and ongoing maintenance to keep infrastructure operating and to prevent premature failure including repairs built infrastructure and installed engineering services.

  - Installed Engineering Services are those services that were installed as part of the original building contract.

  - Hospital equipment and the installation of new engineering services and the replacement of major equipment are thus excluded.

  - Responsibilities during the execution of Preventative Maintenance.

    - Office of the Chief Engineer compiles bid and contract documentation. In terms of PTI 16 B the NEC contract is applied.

    - Hospitals are to comply with the requirements of the PFMA and SCM, Regulations.  Facility SCM invites bids via electronic media.

    - Engineering to compile recommendation to Institutional Bid evaluation committee.

    - Institution to issue order to Contractor.

    - Engineering responsible for Contract management to issue site hand-over Certificate, evaluate and approve invoices.

    - Maintenance staff to supervise contractor. E.g. inspection of works, signing off of works orders etc.

    - In accordance with contract, Contractor may proceed with remedial work up to a value of R 1000-00, at contracted rates, while performing inspections and services.

    - Contractor should provide quotations for any work above R1000-00 (at billed rates) for approval by Engineering before embarking on any remedial work.

    - Invoices to be paid by facility and claimed back from Preventative maintenance Program 8 Preventative maintenance

    - Claim Back Procedure for Preventative Maintenance

      - Written agreement must be obtained from the Directorate: Engineering that Program 8 funding can be utilized towards the specific maintenance requirement. See Forms Annexure to Fin448 Pages 18 &19 of this document

      - Record must be maintained at institutional level of expenditure.

      - Regions/Institutions must claim all monies paid to suppliers in respect of the above from Program 8 Preventative Maintenance

      - Once the work has been completed, a claim as per the following process must be submitted to the Assistant Director: Accounting, 19th Floor, Tower Block.   The Chief Directorate: Financial Management will ensure that the necessary expenditure be effected against Program 8.

      - Regions/Institutions must claim all monies paid to suppliers and/or goods used in respect of the above from the Directorate: Financial Accounting by means of a Fin. 448 form.

      - The completed Fin. 448 form, together with certified copies of the invoices and the BAS Sundry Payment (PGWC 013) must be submitted to -

The Director: Financial Accounting

Department of Health

P O Box 2060

CAPE TOWN

8000

(For attention: Mr D Hendricks Financial Accounting, 19th Floor, 4 Dorp Street).

      - The following allocation codes are to be used when completing the Fin. 448 form:

Fund:	Assets & Liabilities

Responsibility:	Financial Admin (H/O)

Objective:	Liabilities

Item:	Inter Respons Clearing Acc: CL

Project No: No PRJ:STND/A Liability

Net Asset: Non Asset Related

Regional ID: No Regional ID

For enquiries: Contact person: Mr Tasleem Jackson – 021 – 483 4666

Mr Delmaine Hendricks – 021 – 483 -4398

Special note -

      - The Directorate Financial Account will only honour claims which are submitted within two months of receipt of invoice.

      - All Claims shall be submitted within 30 days of payment.

      - All claims must be submitted before the end of the financial year.

      - A copy of this Claim Back Procedure must be attached to the claim.

- Maintenance Work by the Department of Transport and Public Works

  - The Department of Transport and Public Works conducts full facility condition assessments which indicates priority levels.

  - Directorate Infrastructure Planning compiles a schedule of priority maintenance projects.

  - Consultation regarding this list takes place at the IDPMT meetings.

  - A list is compiled for a three yearly cycle (MTEF Period)

  - The final list is published annually in the UAMP

| ANNEXURE 1 FAX / FAKS | PROVINCIAL ADMINISTRATION: WESTERN CAPE Department of Health - Directorate Engineering _______________________________________________________________________________________________ PROVINSIALE ADMINISTRASIE: WES-KAAP Departement van Gesondheid - Direktoraat Ingenieurswese |
| --- | --- |

| Date & time of emergency | D D | M M | Y Y | Time |
| --- | --- | --- | --- | --- |

REQUEST FOR EMERGENCY REPAIR WORK

| TO / AAN: |  | FROM / VAN: |  |
| --- | --- | --- | --- |
| - FAX / FAKS | (021) 918-1690 | - FAX / FAKS |  |
| Directorate Engineering - Direktoraat Ingeneurswese |  | INSTITUTION INSTITUUT |  |
| FOR ATTENTION VIR AANDAG | C Badenhorst H Grebe | ENQUIRIES NAVRAE |  |
|  |  | TELEPHONE TELEFOON |  |
| NO. OF PAGES GETAL BLADSYE |  | DATE DATUM |  |

NATURE OF EMERGENCY:

ACTION TAKEN:

NAME OF CONTRACTOR:                   			TEL. NO.:

ESTIMATE OF COST:

FIN 448 REFERENCE NUMBER:

FURTHER ACTION REQUIRED:

ASSISTANCE REQUESTED BY:  ______________________________

PERSON CONTACTED:  C Badenhorst

OFFICE USE:

| Authorised by | Name |  | Sign |  | Date |
| --- | --- | --- | --- | --- | --- |
| Entered onto Database |  | By: |  | Date: |  |

NAME:  ______________________________

- Please attach this signed annexure 1 to any claim against Program 7.2 funds as per paragraph 6.3 of the Protocol.

|  | Emergency Repair Work | ANNEXURE 2 |
| --- | --- | --- |

| NO. | NAME OF COMPANY | CONTACT NAME | TEL. / CELL | NATURE OF WORK |
| --- | --- | --- | --- | --- |
| Auto claves |  |  |  |  |
|  | Metro Hospital Services | Martin Odendal | (021) 906-4375 | Steam generators and autoclaves |
|  | Rob Dyer Surgical | Patrick Dyer | (021) 555-1760/ 082 575 3834 | Steam generators and autoclaves |
|  |  | Trevor Dyer | 082 770 7665 | Steam generators and autoclaves |
|  | Hospi Sterilizers | Christo Swanepoel | 082 456 1112 | Steam generators and autoclaves |
|  | Ottomatic | HK Otto | 083 261 5047 | Autoclaves, BMS |
| Standby Generators |  |  |  |  |
|  | Altilech | Pieter Saayman | (021) 872 0102/082 325 0244 | Generators/Electrical, Metro Pole |
|  | Ed Power | Reg Holder | 082 804 1880 | Standby generators & electrical, All regions except Eden & Karoo |
|  | Dhanesh Electrical | Anil Jessa | (021) 930 7621/084 733 5306 | Generators, Electrical/Refrigeration, Air conditioners, Metro Pole |
|  | Emergency Power Services | Johann vd Berg | (044) 875 0242/084 512 7334 | Standby generators – Southern Cape, Eden Karoo |
|  | PTI Engineering | Mattie | 021 552 6026 | Standby Generators |
| Electrical |  |  |  |  |
|  | Southern Projects | S Peterson | (021) 393 1163 | Electrical |
|  |  | Emile Langson | 083 762 5419 | Electrical |
|  | Riversdal Electrical | Kobus Coetzee | O79 524 2971 | Electrical + High tension Southern Cape, Karoo, Eden. HT Western Cape |
|  | Southern Star Electrical | Morne’ de Villiers | 082 901 1658 | Electrical |
|  | Altilech | Pieter Saayman | (021) 872 0102/082 325 0244 | Generators/Electrical |
|  | Electrofit | André Saayman | 082 444 4838 | Electrical + HT |
|  | Monte Vista Electrical | David Jones | 083 251 5458 | Electrical (closed December) |
| Plumbing & Burst pipes |  |  |  |  |
|  | Warren Plumbers | Warren | 082 921 3662 | Plumbing |
|  | RMI | Ismael | 082 498 0066 | Plumbing |
|  | Plumbing for Africa | Barry | (021) 7019299 / 082 4164807 | Plumbing/Burst water mains |
|  | BLT | Yvonne/ Trevor | (021) 905 3744/ 083 4575601 | Burst water lines, fitters, boiler house repairs |
|  | Smitson Engineering | Marchel | (021) 939-4336 | Burst water lines, fitters, boiler house repairs |
|  | Roto Rooter | Diverted Calls | (021) 551-2316 | Blocked drains / plumbing |
|  | Turbo Seal | Bruever Visser | (021) 905-6346/ 071 1343702 | Blocked drains / plumbing/Burst water mains |
|  | Idas Construction | Edmund | (021) 886 5056/0710653652 | Blocked drains / plumbing/Burst water mains |
|  | Petersen Plumbing | Galiet Petersen | (021) 697 2294/0837652440 | Blocked drains / plumbing/Burst water mains |
|  | NH Plumbers | Mr Hendricks | 0823462680 | Blocked drains / plumbing/Burst water mains Small Jobs. |
| Air-conditioning & Refrigeration |  |  |  |  |
|  | CAS Air conditioners | H Grobelaar | 083 3799801 | Chillers, Air conditioners, Refrigeration |
|  | Apollo Air | Carlo | 083 462 8053 | Chillers |
|  | RIC | Marius | 082 4444317 | Chillers, Air conditioners, Refrigeration |
|  | Larry’s Air conditioning | Larry Damonze | 082 329 4407 | Chillers, Air conditioners |
|  | Multicool | Marius Ras | (021) 939 3509/ 084 6568755 | VRV |
|  | SFI | Eward Hector | 086 0555734/ 086 0111734 | Chillers, Air conditioners, VRV |
|  | Cold Fact | Jaques Mouton | (021) 862 4705/ 083 2853479 | Chillers, Air conditioners |
|  | Fridge and Freezer Repairs | Rudolf Brits | 082 466 7150 | Refrigeration |
|  | B Kool | Patrick | (021) 592 4256 | Refrigeration Southern Suburbs |
|  | Jc Refrigeration | Marius Feyt | (021) 932 9780/071 4949109 | Refrigeration |
|  | AMT Systems | Gerrit Carstens | 082 8889190 | Chillers, Air conditioners, Refrigeration + Heat Pumps Eden Karoo |
|  | F& A Air-conditioning | Gareth Fife | 044 8736584/ 082 4522788 | Chillers, Air conditioners, Refrigeration Eden |
|  | Karoo Lugverkoeling | Paul Abraham | 082 788 1763 | Chillers, Air conditioners, Refrigeration Karoo |
|  | Heat and Energy | Mike Jonker | 082 974 0516 | Heat pumps and air conditioning |
|  | Tekni Heat | Lawrence Low | 082 498 7429 | Heat Pumps |
| Roofing & Building |  |  |  |  |
|  | Jamo Construction | Jamiel Panday | 023 3423373/076 472 8496 | Roofs and general builder’s work |
|  | YRK Civil Projects | Robbie Kruger | (021) 9887223/084 630 3979 | Roofs and general builder’s work |
|  | AJ Smith Construction | B Smith | (021) 9004451/076 152 4258 | Roofs and general builder’s work |
|  | Roof Repairs | Michael Roberts | (021) 762-1763 | Roof repairs |
|  | Keep Electronics | Mark Jones | (021) 702 1102 | Fire Alarm System |
|  | AC Flooring | Lyndon | 082 788 7889 | Flooring |
|  | Southern Projects | S Peterson | (021) 393 1163 | Roofs and general builder’s work |
|  |  | Emile Langson | 083 762 5419 | Roofs and general builder’s work |
|  | Riversdal Electrical | Kobus Coetzee | O79 524 2971 | Roofs and general builder’s work Southern Cape, Karoo, Eden. |
|  | Phase Electrical | Mr Fouten | 705-0639/072 200 0324 | Electrical |
|  | Raycon Properties | Nasief | 083 258 7688 | Building |
| Cleaning & General |  |  |  |  |
|  | Aurus Logistics | Ronnie | 083 2380601 | Cleaning, tree felling |
|  | Peter & Lena Cleaning | Lena | 078 065 0507 | Cleaning |
|  | Pam care property services | Kurt | (021) 903 6975/ 076 740 3565 | Cleaning, minor building works |
|  | Sankofa Cleaners | Nomveliso | 078 235 1338 | Cleaning |
|  | Build up cleaning services | Florence Komani | 078 553 6217 | Cleaning, minor building works |
| Boilers and steam installations and repairs |  |  |  |  |
|  | BLT | Yvonne/ Trevor | (021) 905 3744/ 083 4575601 | Boilers & Steam |
|  | Hot & Cool Engineering | Glen Gaffley | (021) 703 2833/082 576 2548 | Boilers & Steam |
|  | WP Mechanicals | Vincent Gaffley | 083 423 1343 | Boilers & Steam |
|  | Smitson Engineering | Marchel | (021) 939-4336 | Burst water lines, fitters, boiler house repairs |
| Medical Gas |  |  |  |  |
|  | RJ Mechanicals | Kevin Rolls | 083 230 0924 | Medical gas & Vacuum |
|  | Medical Gas Solutions | Desmond Naude | 083 651 9400 | Medical gas & Vacuum |
|  | DMJ Mechanicals | Dominique Josse Denzil Mclean | 083 228 2421 078 571 1877 | Medical gas & Vacuum |
| Fire alarm & Access control |  |  |  |  |
|  | Firetech Projects CC | Carl Roberts | 021 919 5915 / 083 406 0390 | Fire Alarms, Access Control (Cape Town) |
|  | ITS Technologies | Carlo Kotze | 021 551 8097 / 082 793 5302 | Fire Alarms, Access Control (Cape Town) |
|  | Secure Electronics | Ishmaeel Davids | 021 802 6151 / 082 379 9928 | Fire Alarms, Access Control (Cape Town) |
|  | Techris Technical Solutions | Clint Williams | 021 706 1043 / 071 947 9664 | Fire Alarms, Access Control (Cape Town) |
|  | R&T Security | Ferdi Rhoode | 044 878 0812 / 083 288 8639 | Fire Alarms, Access Control (George) |
|  | Chubb Security George | Lesley Anne | 044 801 7200 / 082 379 5482 | Fire Alarms, Access Control (George) |
| Air-conditioning Controls (BMS) |  |  |  |  |
|  | Ottomatic | HK Otto | 083 261 5047 | BMS |
|  | Cape Automation | Robert Lock | 082 770 9702 | BMS, Johnson controls |
|  | Motor Control Cape | Basil Thompson | 083 261 7283/ 082 822 3920 | BMS, Steafa, Siemens |
|  | James Refrigeration | Douglas James | (021)762 6912/082 777 5800 | BMS, Staefa |

# ANNEXURE 3

# MAINTENANCE WORK:  PRIORITY CATEGORIES

## A Priority

Work necessary to:

- Correct or prevent a dangerous situation.

- Prevent a potentially unsafe situation.

- Repair or replace an essential installation has broken down.

- Repair or replace an essential installation that is about to break down.

- Comply with the Occupational Health and Safety Act.

## B Priority

Work necessary to:

- Prevent costly deterioration / damage to a structure or installation.

- Prevent serious financial loss from continuing to operate inefficient machinery.

- Prevent a building from becoming a health risk.

## C Priority

Work necessary to:

- Maintain buildings and structures in an acceptable condition.

- Maintain an environment conducive to good patient care.

- Maintain a pleasant working environment.

- Maintain the appearance of buildings and structures (image of the Department).

## D Priority

Work that can be delayed until the next financial year.

| ANNEXURE TO FIN 448 FAX / FAKS | PROVINCIAL ADMINISTRATION: WESTERN CAPE Department of Health - Directorate Engineering _______________________________________________________________________________________________ PROVINSIALE ADMINISTRASIE: WES-KAAP Departement van Gesondheid - Direktoraat Ingenieurswese |
| --- | --- |

REQUEST FOR unscheduled PREVENTATIVE MAINTENANCE WORK

| TO / AAN: |  |  | FROM / VAN: |  |  |
| --- | --- | --- | --- | --- | --- |
| ##### FAX / FAKS | (021) 918-1690/ 1605 |  | ##### FAX / FAKS |  |  |
| Directorate Engineering ###### Direktoraat Ingeneurswese |  |  | INSTITUTION INSTITUUT |  |  |
| FOR ATTENTION VIR AANDAG |  | H Grebe CF Badenhorst | ENQUIRIES NAVRAE |  |  |
| FIN REFERENCE NUMBER: |  |  | TELEPHONE TELEFOON |  |  |
| NO. OF PAGES GETAL BLADSYE |  |  | DATE DATUM |  |  |

NATURE OF Work:

NAME OF CONTRACTOR:  ________________________	TEL. NO.:  __________

ESTIMATE OF COST:

FURTHER ACTION REQUIRED:

FIN 448 REFERENCE NUMBER: ______________________________

ASSISTANCE REQUESTED BY:  ______________________________

PERSON CONTACTED:  ______________________________

OFFICE USE:

| Authorised by | Name |  | Sign |  | Date |
| --- | --- | --- | --- | --- | --- |
| Entered onto Database |  | By: |  | Date: |  |

NAME:  ______________________________

Please attach this signed annexure to any claim against Program 8 Preventative Maintenance as per paragraph 7.4 of the Protocol

| ANNEXURE to FIN 448 FAX / FAKS | PROVINCIAL ADMINISTRATION: WESTERN CAPE Department of Health - Directorate Engineering _______________________________________________________________________________________________ PROVINSIALE ADMINISTRASIE: WES-KAAP Departement van Gesondheid - Direktoraat Ingenieurswese |
| --- | --- |

REQUEST FOR reimbursement PREVENTATIVE MAINTENANCE EXPENDITURE

| TO / AAN: |  | FROM / VAN: |  |
| --- | --- | --- | --- |
| ##### FAX / FAKS | (021) 918-1690 | ##### FAX / FAKS |  |
| Directorate Engineering ###### Direktoraat Ingeneurswese |  | INSTITUTION INSTITUUT |  |
| FOR ATTENTION VIR AANDAG | H Grebe C Badenhorst | ENQUIRIES NAVRAE |  |
| FIN REFERENCE NUMBER: |  | TELEPHONE TELEFOON |  |
| NO. OF PAGES GETAL BLADSYE |  | DATE DATUM |  |

| Contract and Bid no |  | Order number |  |
| --- | --- | --- | --- |
| Service |  |  |  |
| Contract Amount |  |  |  |

| Invoice No | Date of Invoice | Amount Incl VAT |
| --- | --- | --- |
| 302 - progress claim 1 |  | R150 000.00 |

NAME OF CONTRACTOR: 	TEL. NO.:

FIN 448 REFERENCE NUMBER:

APPROVAL REQUESTED BY: ______________________________

PERSON CONTACTED:  H Grebe 021 – 918 1702   ___________________

OFFICE USE:

| Authorised by | Name |  | Sign |  | Date |
| --- | --- | --- | --- | --- | --- |
| Entered onto Database |  | By: |  | Date: |  |

NAME:  ______________________________

Please attach this signed annexure to any claim against Program 8 Preventative Maintenance as per paragraph 7.4 of the Protocol